Design Project Plan

SilqQMS Electronic Document Management System Transition Plan

# Purpose

## The purpose of this design control project plan is to define the activities, reviews, deliverables, and resources necessary to transition SILQ's quality document operations from the FileHold document management system to the SilqQMS electronic document management system. This plan ensures the transition is conducted in compliance with QM.SLQ005 (Design Project Planning SOP), QM.SLQ001 (Document Control SOP), ISO 13485:2016, Medical Devices — Quality Management Systems, and 21 CFR Part 820 Quality Management System Regulation

# Scope

## This document is the QMS platform transition plan for moving SILQ's quality document operations from the FileHold document management system to the SilqQMS electronic document management system. Because many current QM procedures explicitly describe FileHold specific workflows, every FileHold reference must be evaluated and updated.

## SilqQMS software validation is being conducted per QM.SLQ032 (Software Validation SOP) and is documented in the SW.SLQ007–012 validation deliverable series. The activities described in this transition plan are to be initiated upon completion of the SilqQMS validation

# Documents

## Reference Documents

### QM.SLQ001	Document Control SOP

### QM.SLQ004	Design Control Program SOP

### QM.SLQ005	Design Project Planning SOP

### QM.SLQ014	Electronic Document System Work Instruction

### SW.SLQ007	Software Validation Plan, SilqQMS

### SW.SLQ008	Product Requirements Specification, SilqQMS

### SW.SLQ009	Software Validation Plan, SilqQMS

### QM.SLQ032	Software Validation SOP

### 21 CFR Part 820	Quality Management System Regulation (QMSR, as revised — incorporates ISO 13485:2016 by reference)

### ISO 13485:2016, Medical Devices — Quality Management Systems — Requirements for Regulatory Purposes (clause 4.1.6, Validation of QMS software)

## Appendices / Associated Forms

### Appendix A: QMS Transition Plan: FileHold to SilqQMS (detailed transition analysis with document-by-document disposition)

# Definitions

## Abbreviations / Acronyms

### DCO: Document Change Order

### EDMS: Electronic Document Management System

### DHF: Design History File

### EDMS: Electronic Document Management System

### QA: Quality Assurance

### QMS: Quality Management System

### QMSR: Quality Management System Regulation

### RA: Regulatory Affairs

### SOP: Standard Operating Procedure

### WI: Work Instruction

## General Definitions

### SilqQMS: A custom-developed, web-based electronic document management system (EDMS) used by SILQ to store, organize, retrieve, and lifecycle-manage controlled QMS documents and records.

### FileHold: Software-based document management system previously used to electronically store controlled documents.

### Document Change Order (DCO): The form used to add new or change existing documents in the document control system, per QM.SLQ001.

### Design History File (DHF): A compilation of records that describes the design history of a finished device or system.

# Product Overview

## SILQ's existing quality procedures are well-structured, operationally detailed, and reflect years of established practice. However, many procedures describe FileHold-specific workflows and UI mechanics. As SILQ transitions its electronic document management to SilqQMS, these procedures must be updated to reflect the new system's operations.

## SilqQMS is a custom-developed, web-based EDMS that acts in support of SILQ's paper-based QMS. Documents are authored and approved outside of SilqQMS (per QM.SLQ001 Document Control SOP) and uploaded to SilqQMS for controlled storage, revision tracking, and retrieval. The SilqQMS validation is being conducted per QM.SLQ032 and is documented in the SW.SLQ007–012 validation deliverable series. The system provides: Controlled document storage with formal revision tracking (Draft → Released → Obsolete lifecycle), Eleven browsable document libraries organized by QMS subsystem, Append-only audit trail for compliance evidence, Role-based access control for document security

## The transition described in this plan consists of updating QMS procedure text to replace FileHold-specific instructions with SilqQMS-equivalent operations. It does not change the substance of SILQ's quality procedures — only how they describe the system used to manage documents.

# Product Quality

## Project will be implemented to provide deliverables in compliance with the regulations set forth in ISO 13485:2016 (Medical Devices — Quality Management Systems — Requirements for Regulatory Purposes) and 21 CFR Part 820, Quality Management System Regulation (QMSR, as revised — incorporates ISO 13485:2016 by reference).

# Key Milestones

## This project consists of five sequential phases following the completion of SilqQMS software validation (SW.SLQ007–012):

### Phase 1A QM Document Major Revisions: Complete rewrite of the two procedures with deep FileHold dependency (QM.SLQ014, QM.SLQ001). These are the foundational documents that define system workflows and document control operations. Completing these first establishes shared transition language for subsequent phases.

### Phase 1B QM Document Targeted Revisions: Line-by-line review and revision of six procedures with multiple embedded FileHold references in process steps (QM.SLQ003, QM.SLQ017, QM.SLQ020, QM.SLQ036, QM.SLQ015, QM.SLQ004). Each parent SOP revision includes review of associated forms and templates.

### Phase 2 QM Document Minor Revisions: Batch review and update of 25 procedures with 1–2 FileHold references (typically glossary definitions and records-filing sentences).

### Phase 3 Data Migration: Transfer of existing files, records, and document archives from FileHold into SilqQMS.

### Phase 4 Employee Training: Training of all personnel on revised quality system procedures and the SilqQMS system

# Key Resources

## Ethan Rao (QA/RA/R&D) will perform the activities described in this transition plan. Activities in Phases 1A, 1B, 3, and 4 will be reviewed by appropriate Silq Management personnell

# Project Activities, Reviews and Deliverables

## The Silq 2026 Electronic Document Management System Transition Plan is a combination of the activities described in Table 1

## The following table details the activities reviews, and deliverables required for each phase of the design control project.  Activities and deliverables are not limited to only those listed in the table.  The status of each item listed in the table will be updated as the project unfolds.

Table 1: Design Control Project Activities, Reviews, and Deliverables for Design Project Plan, Silq EDMS Transition

| Project Phase | Activity or Deliverable | Required Review | Estimated Date | Responsible Party | Status | Comments / Additional Information |
| --- | --- | --- | --- | --- | --- | --- |
| Phase 0: Project Planning | Approve the following documents through DCO: DC.SLQ001 Design Project Plan, SilqQMS EDMS Transition, SW.SLQ007–012 (SilqQMS Software Validation and Verification Documents) | Yes | 07 Apr 2026 | Ethan Rao | In Process |  |
| Phase 1A: QM Document Major Revisions | Complete comprehensive revision of procedures and associated documents with embedded FileHold Operations. - QM.SLQ014 Rev B - Electronic Doc System WI - FM1-QM.SLQ014 - QM.SLQ001 Rev A - Document Control SOP - FM1-QM.SLQ001, FM2-QM.SLQ001, TMP1-QM.SLQ001 | Yes | 15 Apr 2026 | Ethan Rao | Initiate upon completion of Phase 0 |  |
| Phase 1B: QM Document Targeted Revisions | Complete line by line review and revision of procedures and associated documents with multiple FileHold references - QM.SLQ003 Employee Training SOP - FM1-QM.SLQ003, FM2-QM.SLQ003 - QM.SLQ017 Internal Audits SOP - QM.SLQ020 Purchasing Controls SOP - FM1-QM.SLQ020 - QM.SLQ036 Sales Order SOP - QM.SLQ015 Supplier QA SOP - QM.SLQ004 Design Control Program SOP | Yes | 01 May 2026 | Ethan Rao | Initiate upon completion of Phase 1A |  |
| Phase 2: QM Document Minor Revisions | Complete review and revision of procedures and associated documents with 1-2 FileHold references (typically in definition section) QM.SLQ005 Design Project Planning SOP, QM.SLQ006 Design Input SOP, QM.SLQ007 Design Output SOP, QM.SLQ008 Design Review SOP, QM.SLQ009 Design VV SOP, QM.SLQ010 Design Transfer SOP, QM.SLQ012 Risk Management SOP, QM.SLQ013 Risk Analysis SOP, QM.SLQ016 CAPA SOP, QM.SLQ018 Management Review SOP, QM.SLQ021 Product Complaint System SOP, QM.SLQ023 eMDR Submission Work Instruction, QM.SLQ028 Protection of Confidential Patient Info, QM.SLQ029 DHR Review and Approval SOP, QM.SLQ030 Advisory Notices and Recalls SOP, QM.SLQ038 Managing Regulatory Inspections, QM.SLQ043 Work Order SOP, QM.SLQ046 Shipping SOP, QM.SLQ048 Device Master Record SOP, QM.SLQ051 Environmental Monitoring, QM.SLQ027 Quality Manual, QM.SLQ039 Receiving Inspection SOP, QM.SLQ045 Receiving SOP, QM.SLQ049 Workstation Practices SOP, QM.SLQ050 Calibration and Preventive Maintenance SOP | Yes | 15 May 2026 | Ethan Rao | Initiate upon completion of Phase 1B |  |
| Phase 3: Data Migration | Move all existing files, records, and document archives from FileHold into SilqQMS. | Yes | 01 Jun 2026 | Ethan Rao | Initiate upon completion of Phase 2 |  |
| Phase 4: Employee Training | Perform employee training on all revised aspects of quality system | Yes | 15 Jun 2026 | Ethan Rao | Initiate upon completion of Phase 3 |  |

Note: Some QM documents identified in this plan may also require regulatory requirement compliance revisions identified in Silq Q2 Quality Plan Gap Analysis