Design Project Plan

Silq 2026 Electronic Document Management System Transition Plan

# Purpose

## The purpose of this design control project plan is to define the activities, reviews, deliverables, and resources necessary to develop and manufacture functional prototypes of the Silq 2026 Electronic Document Management System Transition Plan that are compliant with regulatory standards and defined user requirements.

# Scope

## This document is a QMS platform transition plan for moving Silq's quality document operations from FileHold to SilqQMS Electronic Document Management System. The transition plan is needed because many current QM procedures explicitly describe FileHold-specific workflows. To avoid procedural mismatch and ensure clarity of all quality policy documents, every FileHold reference must be evaluated and updated. The SilqQMS Electronic Document Management System has been validated per QM.SLQ032 A Software Validation SOP

# Documents

## Reference Documents

### <Insert reference documents; however, do not insert general references to regulations.  Reference subparts if possible>

## Appendices / Associated Forms

### <Insert titles of appendices and forms associated with this document>

# Definitions

## Abbreviations / Acronyms

### <Insert any abbreviations or acronyms that appear throughout the document>

## General Definitions

### <Insert any terms in document that require definition or clarification for the reader>

# Product Overview

## Silq’s existing quality procedures are well-structured, operationally detailed, and reflect years of established practice. However, many procedures are only applicable to the FileHold platform and associated UI mechanics. As Silq continues to improve its QMS, it is necessary to transition to a platform with a modernized user interface tailored to Silq’s ongoing activities. The SilqQMS Electronic Document Management System has been validated per QM.SLQ032 A Software Validation SOP and is intended to replace the FileHold Electronic Document Management System. The system will provide controlled document access, approval workflow execution, storage location for records, archives, logs

# Product Quality

## Project will be implemented to provide deliverables in compliance with the regulations set forth in ISO 13485 and 21 CFR Parts 4 and 820 Medical Devices; Quality System Regulation Amendments Final Rule

# Key Milestones

## <Provide a flow diagram of the applicable design phases of the design project>

## <Provide a written summary of overall objectives and critical activities/deliverables for each of the project phase.  Provide notes to highlight additional information to clarify special circumstances of the plan>

# Key Resources

## Ethan Rao (QA/RA/R&D) will perform the activities described in this transition plan. Activities in Phases 1A, 1B, 3, and 4 will be reviewed by appropriate Silq Management personnell

# Project Activities, Reviews and Deliverables

## The Silq 2026 Electronic Document Management System Transition Plan is a combination of the activities described in Table 1

## The following table details the activities reviews, and deliverables required for each phase of the design control project.  Activities and deliverables are not limited to only those listed in the table.  The status of each item listed in the table will be updated as the project unfolds.

Table 1:	Design Control Project Activities, Reviews, and Deliverables for <Insert Name>

| Project Phase | Activity or Deliverable | Required Review | Estimated Date | Responsible Party | Status | Comments / Additional Information |
| --- | --- | --- | --- | --- | --- | --- |
| Phase 1A: QM Document Major Revisions | Complete comprehensive revision of procedures and associated documents with embedded FileHold Operations. - QM.SLQ014 Rev B - Electronic Doc System WI - FM1-QM.SLQ014 - QM.SLQ001 Rev A - Document Control SOP - FM1-QM.SLQ001, FM2-QM.SLQ001, TMP1-QM.SLQ001 | Yes | 15 Apr 2026 | Ethan Rao | In Process |  |
| Phase 1B: QM Document Targeted Revisions | Complete line by line review and revision of procedures and associated documents with multiple FileHold references - QM.SLQ003 Employee Training SOP - FM1-QM.SLQ003, FM2-QM.SLQ003 - QM.SLQ017 Internal Audits SOP - QM.SLQ020 Purchasing Controls SOP - FM1-QM.SLQ020 - QM.SLQ036 Sales Order SOP - QM.SLQ015 Supplier QA SOP - QM.SLQ004 Design Control Program SOP | Yes | 01 May 2026 | Ethan Rao | Initiate upon completion of Phase 1A |  |
| Phase 2: QM Document Minor Revisions | Complete review and revision of procedures and associated documents with 1-2 FileHold references (typically in definition section) QM.SLQ005 Design Project Planning SOP, QM.SLQ006 Design Input SOP, QM.SLQ007 Design Output SOP, QM.SLQ008 Design Review SOP, QM.SLQ009 Design VV SOP, QM.SLQ010 Design Transfer SOP, QM.SLQ012 Risk Management SOP, QM.SLQ013 Risk Analysis SOP, QM.SLQ016 CAPA SOP, QM.SLQ018 Management Review SOP, QM.SLQ021 Product Complaint System SOP, QM.SLQ023 eMDR Submission Work Instruction, QM.SLQ028 Protection of Confidential Patient Info, QM.SLQ029 DHR Review and Approval SOP, QM.SLQ030 Advisory Notices and Recalls SOP, QM.SLQ038 Managing Regulatory Inspections, QM.SLQ043 Work Order SOP, QM.SLQ046 Shipping SOP, QM.SLQ048 Device Master Record SOP, QM.SLQ051 Environmental Monitoring, QM.SLQ027 Quality Manual, QM.SLQ039 Receiving Inspection SOP, QM.SLQ045 Receiving SOP, QM.SLQ049 Workstation Practices SOP, QM.SLQ050 Calibration and Preventive Maintenance SOP | No | 15 May 2026 | Ethan Rao | Initiate upon completion of Phase 1B |  |
| Phase 3: Data Migration | Move all existing files, records, and document archives from FileHold into SilqQMS. | Yes | 01 Jun 2026 | Ethan Rao | Initiate upon completion of Phase 2 |  |
| Phase 4: Employee Training | Perform employee training on all revised aspects of quality system | Yes | 15 Jun 2026 | Ethan Rao | Initiate upon completion of Phase 3 |  |