## 2023
This log documents the numbers assigned to CAPA items as described in QM.SLQ016 and to support tracking of CAPA status.
CAPA Numbers
Issue CAPA Number
CAPA # YY-XXX | Summary of Issue / Opportunity | Initiated By | Initiation Date | Part or Document # | CAPA Status | Date CAPA Section 1 Complete | Date CAPA Section 2 Complete | Date CAPA Section 3 Complete | Date CAPA Section 4 Complete | Date CAPA Section 5 Complete | Date CAPA Section 6 Complete | Date CAPA Closed | Closed By | On time/Late | Notes
001-2025 | Inspection of SLQ-211610SPT Finished Goods | Ethan Rao | 2025-07-30 | SLQ-211610SPT | Verification of Effectiveness (Nov 2025 - Nov 2026) | 2025-07-30 | 2025-08-10 | 2025-08-15 | 2025-11-11 | 2025-11-18 | Expected 17 Nov 2026
002-2025 | MDR Reporting | Ethan Rao | 2025-10-20 | QM.SLQ022 | Verification of Effectiveness (Feb 2026 - May 2026) | 2025-10-20 | 2025-10-20 | 2025-11-15 | 2025-11-20 | 2026-02-25 | Expected 15 Jun 2026
003-2025 | Design Control Process | Ethan Rao | 2025-10-20 | QM.SLQ004, DC.SLQ001 | Corrective Action Plan Implementation (Mar 2026 - Apr 2026) | 2025-10-20 | 2025-10-20 | 2026-03-01 | 2026-03-02 | Expected 31 Apr 2026